# ClaimSense AI — Statement of Work, Pricing & Architecture

FDE Capstone · Milestone W2 (Course Week 14) · Stack A: OpenAI Agents SDK + AWS

Client: AutoSure Insurance, Houston TX (synthetic) · FDE: Pranjal

Submitted 2026-10-09 · SOW-ASI-2026-01 v1.0

Table of Contents

# Summary

| Deliverable required this week | Where |
| --- | --- |
| Statement of Work (2 pages): scope, acceptance criteria, IP and data handling, five-week timeline | Part 1 |
| Pricing decision with documented reasoning and explicit assumptions | Part 2 |
| Architecture diagram: four agents, MCP layer, three mock systems, RAG, auth boundary, human gate | Part 3 |
| Risk register: top 5 with likelihood, impact, mitigation | Part 4 |
| MCP tool contract: typed schemas for all three systems, idempotency rules | Part 5 |
| Synthetic data shapes for all three mock systems | Part 6 |
| AWS setup: S3, Cognito user pool, ECR | Part 7 |

| Key figure |  |
| --- | --- |
| $64,500 | Fee cap (T&M underneath), plus up to $1,500 pass-through at cost |
| ~2 min | Time saved per claim at which the pilot pays back within 12 months |
| 21 / 22 | Labelled eval cases where the gate order alone gives the expected code; the miss needs reading, which is the agents’ job |
| 0 | Schema violations across 109 fixture records converted to the contract shape |

All client data, people and dates belong to the synthetic capstone scenario. Hourly rates are illustrative.

# 1 · Statement of Work

SOW-ASI-2026-01 · between AutoSure Insurance, Houston TX (“Client”) and the FDE engagement team (“Provider”) Version 1.0 · 2026-10-08 · Governs under the Master Services Agreement dated 2026-09-15 · Inherits the Engagement Charter v1.1 (confirmed 2026-10-01)

## 1. Purpose

Build and hand over a claims co-pilot that drafts a first-decision recommendation, with citations, for auto physical-damage claims. A licensed adjuster confirms every recommendation. The pilot shortens the time to a first decision and makes those decisions consistent, while leaving every client system unchanged.

## 2. Scope: in

| # | Deliverable | Week | Acceptance criterion (see §4) |
| --- | --- | --- | --- |
| D1 | Architecture, MCP tool contract, risk register, pricing memo (this week’s pack) | W2 | AC-1 |
| D2 | Four-agent pipeline (Document Intake → Coverage Check → Claim Assessment → Decision Draft) in containers, runnable with one docker compose up | W3 | AC-2, AC-3 |
| D3 | Retrieval over the policy manual; every coverage statement cites a clause id | W3 | AC-4 |
| D4 | CI pipeline: build → eval gate (≥ 85%) → image push to the Client’s ECR | W3 | AC-2 |
| D5 | MCP integration server on AWS Lambda; JWT auth; RBAC for the four CMS groups; audit log | W4 | AC-5, AC-6 |
| D6 | 150-case evaluation suite including adversarial cases; gate green | W5 | AC-2, AC-7, AC-10 |
| D7 | CloudWatch dashboard, one error-rate alarm, one rehearsed incident with written report | W5 | AC-8 |
| D8 | Runbook (add user, roll back, escalate manually, update the policy corpus) and handover session | W5 | AC-9 |

## 3. Scope: out

- Any write to the CMS, the document store or policy admin. The pilot integration has no write tools (DEC-001, DEC-005).

- Liability claims. A first-party claim on a liability-only policy is in scope only as a recommended denial.

- Building or retraining a fraud model. The vendor score is treated as an input.

- Rental reimbursement adjudication (Q-07, closed as out of scope).

- Production claimant data, which stays out until the DPA is signed (§6).

- Payment execution, subrogation, salvage, reserving.

- Production cut-over. The handover includes the cut-over checklist but not the cut-over itself.

Anything not listed in §2 is out of scope. A change goes through §8.

## 4. Acceptance criteria

The Client accepts a deliverable when it meets its criterion, demonstrated live or from CI logs. Criteria come from the Charter’s success criteria, measured on the evaluation set owned by Bob Reyes (DEC-006).

| ID | Criterion | Measured on | Threshold | Charter criterion |
| --- | --- | --- | --- | --- |
| AC-1 | Architecture approved by Security; tool contract approved by IT | Sign-off in the W2 review | Both signed | delivery gate |
| AC-2 | Eval gate, including exact figures | Full suite in CI | ≥ 85% overall; ≥ 90% clear; ≥ 75% edge; net payable and TL ratio equal the deterministic computation in 100% of cases | 2, 6 |
| AC-3 | Four claim types return the expected first decision, including fraud routing | W1-A/D/F/R cases | 4 of 4 types; score ≥ 0.70 routed to SIU in 100%, approved in 0% | 2, 3 |
| AC-4 | Coverage grounding | Every coverage statement across the suite | 100% cite a retrieved clause id; 0 citations from outside retrieval | 4 |
| AC-5 | Two-user RBAC test | Alice (adjuster) and Bob (senior) request the same unassigned claim | Alice 403, Bob 200 | 7 |
| AC-6 | Audit trail | Every MCP call during the AC-5 test | 100% logged with user id, action, resource id, result | delivery gate |
| AC-7 | Safety and the human gate | Adversarial slice (injection, forced auto-decision, leakage); every card | 100% adversarial pass; 0 false approves; confirmation line on 100% of cards; 0 system-initiated state changes | 5, 8 |
| AC-8 | Operability | Incident drill | Error shown on the dashboard, rollback completed, report filed | delivery gate |
| AC-9 | Handover | Runbook walk-through with IT | All four procedures executed once by Client staff | delivery gate |
| AC-10 | Latency | Claim selected → card shown, full suite, 3 runs | p95 < 90 s | 1 |

The Client signs, or lists specific failed criteria, within 3 business days of a demonstration. If the Client does neither, the deliverable is accepted. A failed criterion is re-demonstrated once at no charge.

## 5. Timeline

| Week | Dates (2026) | Milestone | Gate |
| --- | --- | --- | --- |
| W2 | Oct 5 – Oct 9 | SoW, pricing, architecture | SoW signed; AC-1 |
| W3 | Oct 12 – Oct 16 | Production agents | AC-2, AC-3, AC-4, AC-10 on the 22-case set |
| W4 | Oct 19 – Oct 23 | Integration, MCP, RBAC | AC-5, AC-6 |
| W5 | Oct 26 – Oct 30 | Evals, observability, handover | AC-2, AC-7, AC-8, AC-9, AC-10 on the 150-case suite |

Each gate is a 45-minute review with the people named in the RACI. If a Client dependency in §7 arrives late, the gate moves by the same number of business days, at no extra cost.

## 6. Data handling

- Data in use. The de-identified 20-claim export, the 15-policy export, the 74-document inventory and the 12-clause policy manual. All of it is synthetic or de-identified, and no claimant PII is used (DEC-007).

- Location. Client data stays in the Client’s AWS account in us-east-1. Model calls send only the dossier: claim, policy and document fields with the holder name removed, plus the computed figures. The requesting user’s identity is never sent to a model (DEC-005).

- Model vendor. OpenAI, used through the API with no training on Client data. Production data needs a signed DPA and a Security review of this architecture. Neither is in this SoW.

- Secrets. Secrets are kept in AWS SSM Parameter Store as SecureString. No credential is stored in code, images or CI logs.

- Retention. Audit logs are kept for 90 days in CloudWatch. Model inputs and outputs are not retained beyond the request, except for eval runs, which store synthetic data only.

- Return and deletion. At the end of the engagement the Provider deletes every copy of Client data outside the Client’s account and confirms this in writing within 5 business days.

## 7. Client dependencies

| # | Dependency | Owner | Needed by |
| --- | --- | --- | --- |
| CD-1 | AWS account access: ECR, S3, Lambda, SSM, IAM roles, CloudWatch; Cognito, or an approved JWT alternative (DEC-012) | Tom Ngata | W2 Fri |
| CD-2 | CMS and document-store API specifications (needed for the production shapes of the mocks) | Tom Ngata | W3 Mon |
| CD-3 | Bob Reyes: 2 hrs/week labelling eval cases; 30 min at each gate | Dana Whitfield | Weekly |
| CD-4 | Security review slot in W2 and W4 | Marcus Chen | W2 Thu, W4 Thu |
| CD-5 | Policy manual changes frozen for the pilot, or a change notice ≥ 2 business days ahead | Grace Liu | Through W5 |

## 8. Change control

A change request records the change, its reason, the impact on cost and timeline, and which acceptance criteria it alters. The Sponsor approves it in writing before work starts. The usual triggers are a new system, a write integration, a new decision code, a threshold change after W3, or a move to production data. Moving the pilot toward auto-approval also needs Legal and Underwriting sign-off (DEC-001 revisit trigger).

## 9. Intellectual property

- The Client owns the deliverables: code, prompts, eval cases, documents and configuration, once paid for.

- The Provider keeps its pre-existing tools and generic libraries and grants the Client a perpetual, royalty-free licence to use them as part of the deliverables.

- Eval cases and labels built from Client data are Client property. They do not leave the engagement.

- Third-party components (OpenAI API, OpenSearch, AWS services) stay under their own licences and terms.

## 10. Commercials

Time and materials, capped at $64,500 in fees. Pass-through cloud and model costs are capped at $1,500 and billed at cost. Invoiced at the end of each milestone against hours logged. The reasoning and assumptions are in the pricing memo (03_PRICING_MEMO.md), and the fee cap holds while those assumptions do. Payment is due 30 days from invoice.

## 11. Responsibilities and warranty

The system is a recommendation tool. Under CLS-PAY-012 no output from it authorises a payment. Responsibility for every claim decision stays with the confirming adjuster. The Provider warrants that each deliverable meets its acceptance criterion at acceptance. Defects reported within 30 days of final acceptance are fixed at no charge.

## Sign-off

| Role | Name | Signature / date |
| --- | --- | --- |
| Sponsor (Accountable) | Dana Whitfield, Claims Director |  |
| Legal & Procurement | Elena Vasquez |  |
| Security (consulted, AC-1) | Marcus Chen, CISO |  |
| Provider | Pranjal, FDE |  |

# 2 · Pricing

To: Dana Whitfield (Claims Director) · cc: Richard Oyelaran (CFO), Elena Vasquez (Legal) From: Pranjal, FDE · 2026-10-07

## Recommendation

Time and materials with a hard cap: $64,500 in fees, plus up to $1,500 of cloud and model costs passed through at cost. Invoices go out at each milestone, against hours logged. If the work comes in under the cap, AutoSure pays less. If it would go over, the Provider absorbs the difference, unless one of the assumptions below has broken and a change request has been signed.

## Why this model

| Model | Verdict | Reasoning |
| --- | --- | --- |
| T&M with a cap | Chosen | The scope is fixed (five weeks, eight deliverables, one acceptance test). The unknowns are on the Client’s side: CMS API readiness, Cognito availability and labelling time. A cap gives the CFO a ceiling, and T&M under it means AutoSure doesn’t pay a risk premium for unknowns that may never materialise. |
| Fixed price | Rejected | It would need a ~25% risk premium (≈ $70,000) to cover the dependency risk in SoW §7. AutoSure would pay for that risk even if it never materialised. |
| Pure T&M | Rejected | No ceiling, and the CFO asked for a number. |
| Outcome-based (e.g., per minute saved) | Rejected for the pilot | There’s no measured baseline. Inconsistency is “about 1 in 6”, and the volumes were only verified this week (Q-06). An outcome price needs a baseline that both sides trust, and producing that baseline is one of the things the pilot is for. It is offered as an option for the production phase. |
| Per-claim subscription | Deferred | It suits production at ~3,900 claims a month. A five-week pilot on 20 claims doesn’t fit it. |

## Fee build-up

| Role | Hours | Rate | Fees |
| --- | --- | --- | --- |
| Forward-deployed engineer (design, build, integration, handover) | 180 | $225 | $40,500 |
| Eval engineer (W3–W5: suite to 150 cases, adversarial set, CI gate) | 60 | $190 | $11,400 |
| Engagement manager (gates, status, change control) | 18 | $235 | $4,230 |
| Estimate | 258 |  | $56,130 |
| Contingency, 15% |  |  | $8,420 |
| Cap |  |  | $64,500 (rounded) |

Fees by milestone, in the order expected to be invoiced: W2 $9,000 · W3 $18,500 · W4 $13,000 · W5 $15,630 (estimate; actuals billed).

## Pass-through costs (billed at cost, cap $1,500)

| Item | Basis | Estimate |
| --- | --- | --- |
| EC2 t2.medium (runtime + OpenSearch) | ~$0.046/h, stopped outside working hours | $25 |
| Lambda, S3, SSM, CloudWatch, ECR | Pilot volumes are inside free tier or a few cents | $20 |
| Model, eval runs on the small model | ~60 CI runs × 150 cases × ~$0.02 | $180 |
| Model, eval runs on the demo model | ~15 runs × 150 cases × ~$0.14 | $315 |
| Model, development and demos | Allowance | $200 |
| Estimate |  | ~$740 |

The cap is twice the estimate because model prices and token counts per claim are estimates until Week 3 measures them. If they are higher, the first lever is to run more of the eval suite on the small model.

## What production would cost to run (not part of this SoW, for the CFO)

| Item | Assumption | Monthly |
| --- | --- | --- |
| Model calls | 3,880 claims (CMS report, Q-06) × ~$0.14 (four calls on the demo-tier model) | ~$545 |
| Hosting (container, search, Lambda, logs) | Small always-on footprint | ~$400 |
| Run cost |  | ~$945/month ≈ $0.24 per claim |

Break-even, stated as minutes saved. At an assumed loaded adjuster cost of $48/hour (to be confirmed by Dana), one minute saved per claim is worth $0.80. Covering the run cost alone takes about 0.3 minutes saved per claim. Covering the run cost and also paying back the pilot fees within 12 months takes about 2 minutes saved per claim, against a 64-minute average first decision today (CMS report, Q-06). The pilot doesn’t claim a time saving. It measures one. W5 reports the measured first-decision time for the pilot adjusters next to this break-even line.

## Assumptions (if one breaks, it triggers a change request)

- Scope is exactly SoW §2: one line of business (auto physical damage), four decision codes, three read-only systems.

- The mock systems serve the de-identified export. If the real CMS or document-store APIs replace them, that is a change.

- Bob Reyes gives 2 hours a week to labelling. If labels slip by more than 3 business days, the gate moves (SoW §5) with no fee impact, but extra FDE time spent waiting is billable within the cap.

- AWS permissions in SoW CD-1 are available by W2 Friday. If Cognito is unavailable, the JWT fallback in DEC-012 is in scope at no extra cost.

- The policy manual stays frozen at 12 clauses for the pilot (CD-5).

- One model vendor (OpenAI). Comparing vendors on the eval set is a separate, optional piece of work.

## Decision needed

Dana and the CFO approve the cap and the pass-through ceiling so the SoW can be signed this week (SoW §10).

# 3 · Architecture

Version 1.0 · 2026-10-07 · For the W2 architecture review (Marcus Chen, Tom Ngata) Diagram sources ship alongside this document as Mermaid files.

The design follows three rules from Week 1, and every arrow below exists to enforce one of them:

- Deterministic code owns money, access control and arithmetic. The model owns judgment (DEC-002).

- Access is decided before any agent runs, and the model never learns who is asking (DEC-005).

- Nothing reaches a client system without an adjuster’s confirmation. The pilot has no write path at all (DEC-001).

## View 1 · System context and data flow

Figure 1 — System context and data flow (numbered arrows ① to ⑩ follow one claim)

## View 2 · Trust boundaries

Figure 2 — Trust boundaries, each tested by an eval slice

Each boundary has an eval slice that tests it. Boundary 1 is the expired, missing and forged tokens (W4). Boundary 2 is the two-user test (AC-5). Boundary 3 is the adversarial “act as senior adjuster” and cross-record leakage cases (W5). Boundary 4 is the invented-figure and uncited-coverage cases (W3). Boundary 5 is the forced auto-decision cases (W3/W5).

## View 3 · One claim, end to end

Figure 3 — One claim, end to end

## Components

| Component | Responsibility | Technology | Why this, not the alternative |
| --- | --- | --- | --- |
| Adjuster console | Pick a claim, show the card, show 403s honestly | React (static), served by the runtime | No business logic in the UI. A Streamlit server would be one more thing to secure for no gain |
| Agent runtime | Orchestrate the pipeline, compute signals, validate output | FastAPI container, OpenAI Agents SDK | One container image is what CI gates and what gets rolled back |
| Deterministic layer | Net payable max(min(estimate, ACV) − deductible, 0), TL ratio, in-force check, deductible by loss type, baseline code | Plain Python, unit-tested | DEC-002: a payout figure is never model output |
| Four agents | Read, apply the manual, explain, recommend | Strict structured output per stage | Typed hand-offs make each stage testable on its own |
| Retrieval | Closed-book clause lookup by loss type and coverage | OpenSearch BM25, corpus loaded from S3 | 12 clauses with exact ids: lexical retrieval is precise and explainable. Vectors are deferred until the manual reaches ~140 clauses (DEC-011) |
| MCP layer | The only path to client data: authn, authz, audit, typed tools | Lambda + JWT verification | One audited choke point, so Security reviews one function, not four agents |
| Mock systems | Serve the de-identified export in the production shape | CSV → typed records (see 06_SYNTHETIC_DATA_SHAPES.md) | When the real APIs arrive, the contract stays the same and only the adapter changes |
| Identity | Users and the four groups | Cognito user pool; fallback in DEC-012 | Groups map 1:1 to the CMS groups found in discovery |
| Secrets | OpenAI key, JWT secret | SSM SecureString via IAM role | No credential in code, image or CI log |
| CI | Build → eval gate → push | GitHub Actions → ECR | No image reaches ECR unless the gate is green |
| Observability | Audit trail, error rate, latency | CloudWatch Logs, dashboard, alarm | Answers Security’s two W4 questions: who read what, and is it healthy |

## Where this differs from the course reference diagram, and why

| Reference diagram | This design | Reason |
| --- | --- | --- |
| Coverage Check “calculates net payable” | Deterministic layer calculates it; Coverage Check cites it | DEC-002. The W1 dry run showed the uncapped formula is $4,600 wrong on W1-R03 |
| MCP server drawn after Decision Draft | MCP is called before any agent runs, and is the only data path | DEC-005. Access has to be decided before the model sees anything |
| Vector search, text-embedding-3-large | BM25 over clause text | 12 clauses with exact ids. Revisit at scale (DEC-011) |
| Streamlit UI | Static React console | Less attack surface; console reads only the runtime API |
| Guardrails “PII/PHI detection” on every response | Identity and holder name never enter the context; validators on output | It is cheaper and more reliable to keep identity out of the context than to detect it afterwards |

## Non-functional targets (from the Charter)

| Target | Design lever |
| --- | --- |
| p95 < 90 s per claim | Four sequential calls. If the W3 measurement misses the target, Coverage Check and Claim Assessment run in parallel (both need only the Intake output) |
| Cost ≤ $0.20 per claim | Small model for eval runs, larger model for demo and production. The choice is set by configuration and goes through the provider seam |
| Provider swap without rewrite | One adjudicator module imports the vendor SDK (DEC-008) |
| Rules fallback | If the model is unreachable, the card shows the deterministic baseline code, labelled engine: rules |

# 4 · Risk register

Version 1.0 · 2026-10-07 · Owner: FDE · Accountable: Dana Whitfield · Reviewed at every weekly gate

Scoring: Likelihood (L) and Impact (I) on a 1–5 scale. Score = L × I. A risk scoring 12 or more is reviewed at every gate. Residual is the score after mitigation, and it is what we expect to report at W5.

## Top 5

| # | Risk | L | I | Score | Mitigation (what we actually build) | Early warning | Tested by | Owner | Residual |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Model hallucination. The card states a fact, figure or document that isn’t in the claim file. | 4 | 4 | 16 | Figures are computed before the model runs and passed in (DEC-002). An output validator rejects any $ figure not in the dossier and any document id not in the inventory. Strict structured output for each agent. If the model fails or is unreachable, the rules baseline is shown, labelled engine: rules. | Validator rejection rate > 2% of runs in CI | W3 “invented figure” and “phantom document” cases; all expected_net_payable_usd asserts | FDE | 2 × 4 = 8 |
| R2 | Coverage misread. A wrongful denial (litigation exposure) or a wrongful approval (leakage), e.g. approving on a lapsed policy whose status still reads Active. | 3 | 5 | 15 | The in-force check runs on dates, not on the status field (CLS-PER-006, W1 Finding 1). Coverage Check must cite a clause id from the retrieved set, and the validator enforces it (DEC-004). Liability Only on a first-party claim leads to deny, which is only ever a recommendation for a senior to sign (DEC-003). Zero false approves is a release gate (DEC-006). | Any false approve in CI. Citation coverage < 100% | W1-D01…D05, W1-F05, AC-4, AC-7 | FDE; Grace Liu (labels) | 1 × 5 = 5 |
| R3 | Auth failure. An adjuster reads a claim not assigned to them, through the console or by prompting the model. | 3 | 5 | 15 | The JWT is verified in the MCP Lambda. can_read_claim is deterministic and runs before any agent. The model never sees the user or group (DEC-005). The runtime forwards the caller’s own JWT to MCP, so there is no shared superuser token. Every call is audited. The policy tool authorises through a claim the caller can read (contract §3.5). | Any 200 for a cross-assignment read in the W4 matrix test | AC-5 two-user test; W4 4-group × 20-claim RBAC matrix; W5 “act as senior adjuster” cases | FDE; Marcus Chen (A) | 1 × 5 = 5 |
| R4 | Data leak. Claimant data reaches the model vendor, a log, or another user’s session. | 2 | 5 | 10 | De-identified export only until the DPA is signed (DEC-007). The holder name is dropped by the contract, never sent (§3.5). The dossier carries one claim only, so nothing crosses records. Audit logs hold ids, not content. Secrets live in SSM, never in images or CI logs. OpenAI API under no-training terms. | Grep of CI and CloudWatch logs for holder-name or JWT patterns, run at every gate | W5 cross-record leakage cases; log scan at W4 and W5 | FDE; Marcus Chen | 1 × 5 = 5 |
| R5 | Scope creep. Pressure to add auto-approval, write-back to CMS, rental adjudication, or production data within the five weeks. | 4 | 3 | 12 | SoW §3 lists every exclusion. Change control (SoW §8) requires a written impact assessment first. DEC-001 states a measurable revisit trigger, so “not now” comes with a date and a condition. Open questions are closed in writing (Q-07 rental: out). | Any request that starts with “while you’re in there…”. A new item at a gate that isn’t in SoW §2 | Change log; every gate starts by reading SoW §2 | Engagement manager; Dana Whitfield | 2 × 3 = 6 |

## Watch list (below the top 5, tracked)

| # | Risk | L × I | Mitigation |
| --- | --- | --- | --- |
| W1 | AWS lab or account guardrails block a required service (seen in W2: Cognito denied, Lambda denied to role sessions) | 4 × 2 = 8 | DEC-012 JWT fallback with Cognito-shaped claims; permission list sent to IT on day 1 (CD-1) |
| W2 | Latency misses p95 < 90 s with four sequential calls | 3 × 2 = 6 | Measure in W3; run Coverage Check and Claim Assessment in parallel; small model for Intake |
| W3 | OCR backlog: estimates stay Pending, so too many cards say “cannot approve yet” and adjusters lose trust | 3 × 2 = 6 | The card names exactly which document is pending and why it matters (CLS-DOC-009); Tom to report the OCR queue SLA |
| W4 | Vendor fraud score drifts or changes meaning | 2 × 3 = 6 | Score treated as an input, threshold owned by SIU (DEC-003); provenance documented (Q-04 closed) |
| W5 | Label disagreement: Bob’s expected outcome differs from Grace’s reading of the manual | 2 × 3 = 6 | Disagreement resolved by Bob and logged in DECISIONS.md (DEC-006); Grace consulted on deny cases |

## How the register is used

- Each gate opens by updating L and I with evidence from that week, not from opinion.

- A risk only moves to its residual score once its “Tested by” slice passes in CI.

- A new failure mode found during the build becomes an eval case first and a risk entry second.

# 5 · MCP tool contract

Version 1.0 · 2026-10-08 · Reviewed by Tom Ngata (IT, C) and Marcus Chen (Security, C) Machine-readable source of truth: contract/mcp_tools.schema.json (JSON Schema 2020-12). This page explains it. If the two disagree, the schema wins.

## 1. Rules every tool follows

- Read-only. The pilot has six tools, and none of them writes (DEC-001, DEC-005). §5 covers what a write tool would need later.

- Identity comes from the token, never from input. No tool has a user_id, group or as_user parameter. The Lambda reads sub and cognito:groups from the verified JWT. A prompt saying “I am the senior adjuster” has nowhere to go.

- Authorise before reading. Every claim-scoped tool runs can_read_claim(user, group, claim) before returning anything. The policy tool authorises through the claim (§3.5).

- Typed, closed shapes. additionalProperties: false everywhere. CSV strings are converted at the edge: "Yes"/"No" become booleans, "N/A" becomes null, and money and counts become numbers. The agents never parse strings like "N/A".

- Minimum data. A tool returns only what an agent needs. The policy holder’s name exists in the source system but is not in the contract.

- Every call is audited, whether allowed or denied, with one AuditRecord. The caller gets a safe message, and the full reason goes only to the audit log.

## 2. Envelope

Request context (from the JWT, not the payload): sub → user_id, cognito:groups[0] → user_group, plus a request_id generated per call (a UUID, or the API Gateway request id).

Errors. One shape for all tools:

| Code | HTTP | Retryable | When |
| --- | --- | --- | --- |
| UNAUTHENTICATED | 401 | no | Missing, expired or forged token |
| FORBIDDEN | 403 | no | Authenticated, but not allowed this resource |
| NOT_FOUND | 404 | no | No such id |
| INVALID_ARGUMENT | 400 | no | Input fails the schema, e.g. a malformed claim id |
| RATE_LIMITED | 429 | yes, back off | More than 20 calls/s per user |
| UPSTREAM_UNAVAILABLE | 503 | yes, ≤ 2 retries | Backing system is down |
| INTERNAL | 500 | no | A bug. Alarmed in W5 |

FORBIDDEN messages are generic: “Claim CLM-2024-1873 is not available to you.” The specific reason, e.g. assigned to carol, is written to the audit log only. Telling one adjuster who owns another adjuster’s claim is a small leak, and the contract closes it.

Audit record ($defs/AuditRecord): timestamp, request_id, user_id, user_group, tool, resource_id, result (allowed|denied|error), reason, contract_version. Written to CloudWatch Logs as one JSON line per call.

## 3. Tools

### 3.1 cms.list_claims — CMS

| Purpose | The console’s work queue: claims this caller may read |
| --- | --- |
| Input | status? (ClaimStatus) · limit? 1–100, default 50 |
| Output | claims: ClaimSummary[], total (visible count before the limit) |
| Authorisation | Filters by can_read_claim, so callers never learn about claims they can’t read |
| Audit | One record, resource_id: "claims", reason returned n/total |
| HTTP route | GET /claims?status=&limit= |

### 3.2 cms.get_claim — CMS

| Purpose | Full claim record for the dossier |
| --- | --- |
| Input | claim_id (pattern CLM-dddd-dddd) |
| Output | claim: Claim (19 typed fields; see data shapes §1) |
| Authorisation | can_read_claim. Senior adjusters read all; adjusters read their own assignments; fraud investigators read claims with score ≥ 0.50; total-loss appraisers read Escalated claims or estimate ≥ 75% of ACV |
| Errors | 404 if no claim exists. 403 if not permitted |
| HTTP route | GET /claims/{claim_id} |

Example (allowed, Alice reading her own claim):

{ "claim": { "claim_id": "CLM-2024-1800", "policy_id": "POL-TXA-88000", "vehicle_vin": "4T1BF1FK5MU500123",
  "vehicle_year": 2021, "vehicle_make": "Toyota", "vehicle_model": "Camry", "vehicle_acv_usd": 24500,
  "incident_date": "2024-02-14", "incident_type": "Parking lot collision",
  "incident_description": "Claimant reversed out of space; struck by another vehicle. Other driver admitted fault at scene.",
  "damage_description": "Rear bumper assembly, trunk lid, rear parking sensors", "repair_estimate_usd": 3200,
  "injuries_reported": false, "police_report_filed": true, "assigned_adjuster": "alice", "prior_claims_12mo": 0,
  "fraud_risk_score": 0.05, "claim_status": "Approved", "created_at": "2024-02-14T08:00:00Z" } }

Example (denied, Alice reading Carol’s claim):

{ "error": { "code": "FORBIDDEN", "message": "Claim CLM-2024-1873 is not available to you.",
  "request_id": "6f1c0e8a-2b1d-4c47-9d0e-1f3a5b7c9d21", "retryable": false } }

Audit line for the denial: {"user_id":"alice","user_group":"adjuster","tool":"cms.get_claim","resource_id":"CLM-2024-1873","result":"denied","reason":"assigned to carol, not alice", ...}

### 3.3 docs.list_documents — Document store

| Purpose | Document inventory: drives the completeness check (CLS-DOC-009) and the injury inconsistency check (CLS-INJ-008) |
| --- | --- |
| Input | claim_id |
| Output | claim_id, documents: Document[] (with ocr_status), count |
| Authorisation | can_read_claim on the parent claim |
| HTTP route | GET /documents?claim_id= |

### 3.4 docs.get_document — Document store

| Purpose | One document with its OCR text, so Document Intake can read it |
| --- | --- |
| Input | document_id (pattern DOC-ddddd) |
| Output | document: Document + ocr_text. ocr_text is null unless ocr_status is Completed. A pending estimate returns no text, and the agent must say so instead of guessing (CLS-DOC-009) |
| Authorisation | can_read_claim on the document’s parent claim |
| HTTP route | GET /documents/{document_id} |

### 3.5 policy.get_policy — Policy admin

| Purpose | Declarations for the claim’s policy: coverage type, deductibles, period |
| --- | --- |
| Input | claim_id, not policy_id |
| Output | policy: Policy. No holder_first/holder_last (DEC-013) |
| Authorisation | Resolve the claim, run can_read_claim, then return the policy that claim references. A caller can only read a policy through a claim they may read, so browsing policy ids gets them nothing |
| HTTP route | GET /claims/{claim_id}/policy (replaces a bare GET /policies/{id}) |

The reason for this design: a bare get_policy(policy_id) is the obvious one to write, but it lets any authenticated user list every policy holder’s declarations. Anchoring the lookup on the claim reuses the same single authorisation rule.

### 3.6 policy.search_clauses — Coverage knowledge base

| Purpose | Closed-book retrieval over the policy manual for Coverage Check (DEC-004) |
| --- | --- |
| Input | query (3–500 chars) · top_k 1–8, default 4 |
| Output | clauses: Clause[] (clause_id, title, text, score), corpus_version (content hash) |
| Authorisation | Any authenticated user. The manual isn’t claim data, but calls are still audited |
| Served by | The agent runtime’s retrieval index (OpenSearch BM25, loaded from S3), not the Lambda |
| Validator link | The card’s citations must be a subset of the clause_ids returned by this tool in the same run |

## 4. Idempotency

| Operation | Rule |
| --- | --- |
| All six pilot tools | Safe and idempotent, with no side effects except the audit line. Retrying is always allowed for retryable: true errors, with exponential backoff (0.5 s, 1 s) and at most 2 retries |
| Audit append | Keyed on request_id. A retried call that reaches the Lambda twice logs two lines with the same request_id, and the W4 audit query de-duplicates on it. Nothing downstream counts raw lines |
| Pipeline run | Re-running a claim is safe because nothing is written. Two runs can return different wording but must return the same code and figures. Determinism of code and figures is an eval assertion |

## 5. Rules for any future write tool (not in the pilot)

A write tool (e.g. cms.record_recommendation) is a change request (SoW §8) and must meet all of these:

- The client sends an Idempotency-Key (UUID v4) on every write.

- The server stores (key, user_id, request_hash, response) for 24 hours.

- The same key with the same payload returns the stored response and performs no second write.

- The same key with a different payload returns 409 CONFLICT.

- Writes are made by the human confirming in the console, never by an agent. The agent toolset stays read-only (DEC-001).

- Every write has a compensating action defined before release, e.g. a reversal note.

## 6. Versioning

- The contract version appears in every audit record.

- Additive changes (a new optional field, a new tool) are a minor version, and existing callers are unaffected.

- Removing or renaming a field, or tightening a type, is a new major version. v1 and v2 tools run side by side for one release.

- The eval suite pins a contract version, so a contract change can’t silently alter results.

# 6 · Synthetic data shapes

Version 1.0 · 2026-10-08 · Fixtures: claimsense_claims.csv (20), claimsense_policies.csv (15), claimsense_documents.csv (74), policy_corpus/ (12) Checked by build.py: every fixture row is converted with the rules below and validated against contract/mcp_tools.schema.json. The results are in WEEK2_DATA_SHAPE_REPORT.md.

Each system has two shapes. The source shape is what the export (and later the real API) gives us. The contract shape is what the tools return. The mock adapter does the conversion, and when the real API arrives only the adapter changes.

## 1. CMS — claim record

| Field | Source | Contract type | Constraint / example | Notes |
| --- | --- | --- | --- | --- |
| claim_id | string | string | ^CLM-\d{4}-\d{4}$ · CLM-2024-1873 | Primary key |
| policy_id | string | string | ^POL-[A-Z]{3}-\d{5}$ | FK → policy |
| vehicle_vin | string | string | 17 chars, no I/O/Q | Must equal the policy VIN (invariant I-2) |
| vehicle_year | string | integer | 1980–2030 |  |
| vehicle_make, vehicle_model | string | string | non-empty |  |
| vehicle_acv_usd | string | number | > 0 | Must equal the policy ACV (I-3) |
| incident_date | string | date | ISO YYYY-MM-DD | Controls coverage, not policy_status (CLS-PER-006) |
| incident_type | string | string | CMS picklist, 20 values in the export | Mapped to loss_category (§4) |
| incident_description, damage_description | string | string | free text | Untrusted input: may carry prompt injection (W5 cases) |
| repair_estimate_usd | string | number | ≥ 0 | The CMS figure. It can exist with no estimate document (W1 Finding 6) |
| injuries_reported | Yes/No | boolean |  |  |
| police_report_filed | Yes/No | boolean |  |  |
| assigned_adjuster | string | string | user id, ^[a-z][a-z0-9._-]+$ | Drives RBAC. Never sent to the model |
| prior_claims_12mo | string | integer | ≥ 0 |  |
| fraud_risk_score | string | number | 0–1 | Vendor score, refreshed nightly (Q-04) |
| claim_status | string | enum | Approved · Pending Review · Under Investigation · Escalated | Historical, sometimes wrong (W1 Finding 1). An input, not a label |
| created_at | string | date-time | ISO 8601 UTC |  |

## 2. Document store — document record

| Field | Source | Contract type | Constraint | Notes |
| --- | --- | --- | --- | --- |
| document_id | string | string | ^DOC-\d{5}$ |  |
| claim_id | string | string | FK → claim (I-4) |  |
| document_type | string | enum | FNOL_FORM · POLICE_REPORT · DAMAGE_PHOTOS · REPAIR_ESTIMATE · WITNESS_STATEMENT · MEDICAL_REPORT · RENTAL_RECEIPT · PREMIUM_RECEIPT | PREMIUM_RECEIPT isn’t in the export. It was added because eval case W1-F05 needs it: a case the contract can’t serve is a contract bug |
| description | string | string |  | Stands in for OCR text in the mock |
| upload_date | string | date | ≥ incident date (I-5) |  |
| page_count | string | integer | ≥ 1 |  |
| ocr_status | string | enum | Completed · Pending · Failed | Failed is reserved; not in the export |
| uploaded_by | string | string | user id | Not sent to the model |
| ocr_text | — | string ¦ null | get_document only | null unless Completed |

## 3. Policy admin — declarations

| Field | Source | Contract type | Constraint | Notes |
| --- | --- | --- | --- | --- |
| policy_id | string | string | ^POL-[A-Z]{3}-\d{5}$ |  |
| holder_first, holder_last | string | dropped | — | PII. Not in the contract (DEC-013) |
| vehicle_vin, vehicle_year, vehicle_make, vehicle_model, vehicle_acv_usd | string | as in the claim record |  |  |
| coverage_type | string | enum | Full Coverage · Liability Only |  |
| collision_coverage, comprehensive_coverage | Yes/No | boolean |  | Liability Only ⇒ both false (I-6) |
| collision_deductible_usd, comprehensive_deductible_usd | number or N/A | number ¦ null | null iff the coverage is false (I-6) |  |
| liability_limit | 300000/100000 | string | ^\d+/\d+$ | Kept opaque; meaning of the split open with Grace (Q-08). Unused in the pilot |
| medpay_limit_usd | string | number | ≥ 0 |  |
| policy_status | string | enum | Active · Expired · Cancelled | Administrative. Never decides coverage on its own |
| policy_start, policy_end | string | date | start < end (I-7) |  |

## 4. Derived field: loss_category (closes Q-03)

The deterministic layer picks the deductible by loss category: collision losses use the collision deductible and comprehensive losses use the comprehensive deductible (CLS-DED-004). The mapping comes from CLS-COMP-002 and was confirmed by Grace Liu on 2026-10-06.

| loss_category | incident_type values (export + W1 synthetic cases) |
| --- | --- |
| collision | Backing accident · Hit and run · Rear-end collision · Low-speed collision · Multi-vehicle pileup · Parking lot collision · Pothole damage (CLS-COMP-002: “treated as collision”) · Rear-end on highway · Rollover · Side-swipe · Single-vehicle accident · T-bone collision · Underride accident |
| comprehensive | Animal strike · Carjacking · Flood damage · Garage fire · Glass breakage · Hail damage · Storm damage · Theft recovery · Vandalism |

An incident_type that isn’t in this table maps to unknown, which forces flag_review. The code never guesses a deductible.

## 5. Cross-system invariants

build.py checks every invariant on the fixtures. Synthetic records generated for the 150-case suite must pass them too, unless a case breaks one on purpose and says so in its notes.

| ID | Invariant |
| --- | --- |
| I-1 | Every claim’s policy_id exists in the policy table |
| I-2 | Claim vehicle_vin = policy vehicle_vin |
| I-3 | Claim vehicle_acv_usd = policy vehicle_acv_usd |
| I-4 | Every document’s claim_id exists in the claim table |
| I-5 | No document is uploaded before its claim’s incident date |
| I-6 | Liability Only ⇒ no collision or comprehensive coverage, and deductibles are null |
| I-7 | policy_start < policy_end |
| I-8 | Every claim has exactly one FNOL_FORM |
| I-9 | Every incident_type maps to a loss_category |
| I-10 | assigned_adjuster and uploaded_by are known users in the identity pool |

## 6. Rules for generating more synthetic cases (W3 → 150 in W5)

- Start from a real fixture and change one thing. Each generated case names its parent claim and the single field it changes, e.g. incident_date moved one day past policy_end. When the case fails, the cause is obvious.

- Hit the thresholds exactly. Fraud scores 0.69 / 0.70 / 0.71, TL ratios 0.74 / 0.75 / 0.76, net payable $24,999 / $25,000 / $25,001, incident on policy_end (in force) and on policy_end + 1.

- Untrusted text goes only where text lives. Prompt-injection payloads go in incident_description, damage_description and ocr_text, the fields an attacker could actually control.

- No realistic PII. VINs are syntactically valid but synthetic. There are no names in any generated record (the policy contract has no name field anyway).

- Labels belong to Bob. The generator proposes the expected outcome, and Bob Reyes confirms it before the case enters the gate (DEC-006).

# 7 · AWS setup and evidence

The curriculum asks for “S3 buckets, Cognito user pool and ECR repos. Three CLI commands. Confirm everything is wired before next week.” The model solution goes slightly further: each command is idempotent, the bucket is private and encrypted, and the evidence is captured by a read-only script rather than by screenshots alone.

Scripts: ../aws/aws_setup.sh (creates resources, safe to re-run) · ../aws/aws_evidence.sh (read-only, writes aws/evidence/<timestamp>/)

## The three resources

| Resource | Name | Why it exists now | Used in |
| --- | --- | --- | --- |
| S3 bucket | claimsense-docs-<account-id> | Holds the policy corpus that retrieval loads at boot. Bucket names are global, so the course’s bare claimsense-docs will collide; the account suffix makes it unique | W3 (aws s3 sync policy_corpus/ …), W5 runbook “update the corpus” |
| Cognito user pool | claimsense-users, groups adjuster, senior-adjuster, fraud-investigator, total-loss-appraiser | The four CMS groups from discovery become the four token groups | W4 JWT authorizer, two-user test |
| ECR repository | claimsense/agents (scan on push, immutable tags) | CI pushes here only after the eval gate passes | W3 CI, W5 rollback |

The course’s raw commands, for comparison:

aws s3 mb s3://claimsense-docs
aws cognito-idp create-user-pool --pool-name claimsense-users
aws ecr create-repository --repository-name claimsense/agents

The script adds four things the raw commands leave out: a unique bucket name, a public-access block and encryption on the bucket, the four groups in the pool, and scan-on-push with immutable tags on ECR.

## Recorded result (reference build, lab account, us-east-1)

| Resource | Result | Evidence |
| --- | --- | --- |
| S3 | Created | get-bucket-location, get-bucket-encryption |
| ECR | Created | describe-repositories shows the repository URI |
| Cognito | AccessDenied by an account-level policy | The denial message itself, kept as evidence. DEC-012 records the fallback; Q-10 asks IT to lift the deny |

Lab accounts carry guardrails. The ones observed in the reference account were: Cognito, API Gateway and the Budgets API are denied; only the t2 instance family can be launched; Lambda is denied to assumed-role sessions. A denial is a finding, not a failure. The milestone evidence is the attempt, the exact error, the region, and the decision recorded in response.

# Appendix A · Decisions (Week 2)

The Week 1 log (DEC-001 … DEC-008) is unchanged. These entries are appended to it. Same rules apply: entries are append-only, every decision names the eval cases that test it, and reversing a decision means adding a new entry.

| ID | Decision | Status | Date |
| --- | --- | --- | --- |
| DEC-008 | Stack A: OpenAI Agents SDK on AWS, behind a provider seam | Accepted (was Proposed) | 2026-10-07 |
| DEC-009 | Gate order: fraud → coverage → total loss → documentation → first-pass band | Accepted | 2026-10-06 |
| DEC-010 | Deductible chosen by loss category; unknown category → flag_review | Accepted | 2026-10-06 |
| DEC-011 | Lexical (BM25) retrieval for the 12-clause manual; vectors deferred | Accepted | 2026-10-07 |
| DEC-012 | Identity: Cognito user pool; fallback to signed JWTs with Cognito-shaped claims if the account denies Cognito | Accepted | 2026-10-08 |
| DEC-013 | Data minimisation in the contract: no holder name; policy is read through a claim | Accepted | 2026-10-08 |
| DEC-014 | Commercials: T&M capped at $64,500 + $1,500 pass-through | Proposed → Sponsor and CFO | 2026-10-07 |

## DEC-008 · Stack A, behind a provider seam — now Accepted

Accepted 2026-10-07 in the architecture review (Tom Ngata, Marcus Chen). Security asked for one change: the model vendor is named in the SoW data-handling clause (SoW §6), and replacing it is a change request.

## DEC-009 · Gate order

Status: Accepted · 2026-10-06 · Bob Reyes (closes Q-01)

Context. CLM-2024-3114 is a garage fire on a Liability Only policy, at 84% of ACV. The Week 1 rule table checks total loss before coverage, which sends this claim to the appraiser. Eve would then value a vehicle that AutoSure doesn’t cover.

Decision. Gates are evaluated in this order, and the first one that fires sets the code:

- Fraud. Score ≥ 0.70 → route_specialist (SIU). Fraud comes first because a fraudulent claim can look covered.

- Coverage. The loss is outside the policy period, the policy is Liability Only on a first-party claim, or the loss category isn’t covered → deny (a recommendation, signed by a senior).

- Total loss. TL ratio ≥ 0.75 → route_specialist (appraiser).

- Injury. Injury reported → flag_review, with the next step “assign an injury-qualified adjuster” (Q-05). route_specialist stays reserved for SIU and the total-loss appraiser, as in DEC-003.

- Documentation. The estimate is missing or pending OCR, a hit-and-run has no police report, or a medical report sits on a no-injury FNOL (CLS-INJ-008) → flag_review.

- First-pass band → approve. Everything else → flag_review.

Consequences. CLM-2024-3114 becomes W2-D06: expected deny, citing CLS-LIAB-003 and CLS-COMP-002, with no appraisal. The Week 3 baseline uses this order.

Dry run (build.py). The gates agree with 21 of 22 labelled cases: the 20 from W1 plus W2-D06 and W2-F06. The one miss is W1-F05, a renewal premium received before the loss but not yet processed. The gates read the dates and say deny. The label says flag_review, because the receipt has to be read. That is the Coverage Check agent’s job, and it’s the reason the agents exist.

Caught by the dry run. Bob’s first answer to Q-05 was “injury → route_specialist”. Run through the gates, that contradicted his own W1-F03 label, and it also contradicted DEC-003, where route_specialist means SIU or the appraiser only. Bob corrected the answer on 2026-10-08 before sign-off. A label set and a rule set that disagree can’t both be the acceptance test, and this check is what found the disagreement.

Tested by. W2-D06, W1-R03 (TL with coverage in force, still routed to the appraiser).

## DEC-010 · Deductible by loss category

Status: Accepted · 2026-10-06 · Grace Liu (closes Q-03)

Decision. loss_category is derived from incident_type using the table in 06_SYNTHETIC_DATA_SHAPES.md §4, which follows CLS-COMP-002. Pothole damage is collision. The deductible is the one for that category. An unmapped type means no deductible is chosen, and the code is flag_review with the reason “unknown loss category”.

Consequences. The export always has equal deductibles, so no fixture changes its figure. W3 adds two synthetic cases with unequal deductibles (one collision, one comprehensive) to prove the deductible is chosen by category.

## DEC-011 · BM25 retrieval, vectors deferred

Status: Accepted · 2026-10-07 · Grace Liu, Tom Ngata

Context. The course reference uses dense vectors. The manual has 12 clauses with exact ids, and adjusters search it by terms (“liability only”, “total loss”, “pothole”).

Decision. OpenSearch BM25 over clause text, loaded from S3 at boot. If OpenSearch is down, the fallback is token-overlap scoring over the same files, so retrieval is still grounded.

Revisit trigger. The manual grows beyond ~60 clauses, or W3 retrieval recall on the 20 cases’ expected_citations is below 95%.

## DEC-012 · Identity provider and the fallback

Status: Accepted · 2026-10-08 · Marcus Chen, Tom Ngata

Context. In the W2 AWS setup, cognito-idp:CreateUserPool returned AccessDenied in the lab account. S3 and ECR worked. See 07_AWS_SETUP_EVIDENCE.md.

Decision. The design uses Cognito: four groups, and an API Gateway JWT authorizer in W4. If the account still denies Cognito at the W4 start, the MCP Lambda verifies HS256 JWTs itself. The secret lives in SSM, and the tokens carry the same claims Cognito would issue (sub, cognito:groups, iss, exp). The authorisation code reads claims, not the issuer, so switching back to Cognito changes configuration only.

Consequences. The two-user test (AC-5) is identical under both. Security accepted the fallback for the pilot only. Production requires Cognito or AutoSure’s IdP.

## DEC-013 · Data minimisation in the tool contract

Status: Accepted · 2026-10-08 · Marcus Chen

Decision. (a) holder_first and holder_last aren’t in the contract, so no tool can return them. (b) The policy is read with policy.get_policy(claim_id) and authorised through that claim. (c) FORBIDDEN messages never name another user, and the detail goes to the audit log only.

Why. Each of these closes a path that a “read-only, RBAC-checked” API would otherwise leave open: holder PII reaching a model, browsing any policy by id, and learning colleagues’ assignments from 403 messages.

Tested by. W4 RBAC matrix (policy through an unreadable claim → 403). W5 leakage cases (the card must not contain a holder name). Contract schema validation (additionalProperties: false).

## DEC-014 · Commercials

Status: Proposed → Dana Whitfield and Richard Oyelaran · 2026-10-07

T&M capped at $64,500 in fees, plus up to $1,500 of pass-through at cost. Reasoning, fee build-up and break-even are in 03_PRICING_MEMO.md.

## Week 1 open questions: closed

| ID | Answer | By | Effect |
| --- | --- | --- | --- |
| Q-01 | Coverage before total loss | Bob Reyes, 2026-10-06 | DEC-009; CLM-2024-3114 → W2-D06 deny |
| Q-02 | Hit-and-run with no police report: flag_review, request the report, approve once filed. “Reasonable proof of loss” (CLS-DOC-009) isn’t met by a photo of a parked car | Bob Reyes, 2026-10-06 | CLM-2024-2165 → W2-F06 flag_review, citing CLS-DOC-009 and CLS-COLL-001 |
| Q-03 | Deductible by loss category per CLS-COMP-002 | Grace Liu, 2026-10-06 | DEC-010 |
| Q-04 | Vendor score: nightly batch, model card received, known weakness on policies under 90 days old | Carol Dimas, 2026-10-07 | Score stays an input; W5 adds a new-policy low-score case |
| Q-05 | Injury → flag_review, next step “assign an injury-qualified adjuster” (in CMS: Escalated, picked up by the injury desk). First answer “route_specialist” corrected 2026-10-08 after the dry run | Bob Reyes, 2026-10-06 / 10-08 | DEC-009 step 4; W1-F03 label unchanged |
| Q-06 | CMS report, Apr–Sep: 3,880 claims/month, 64 min average first decision. The SoW and pricing use these | Dana Whitfield, 2026-10-06 | Pricing memo break-even |
| Q-07 | Rental reimbursement is out of scope | Dana Whitfield, 2026-10-06 | SoW §3 |

## New open questions

| ID | Question | Owner | Needed by |
| --- | --- | --- | --- |
| Q-08 | liability_limit “300000/100000”: which number is per person, per accident, or property damage? It is unused in the pilot but needed before liability is in scope | Grace Liu | Before any liability scope |
| Q-09 | Loaded adjuster cost per hour for the break-even line (memo assumes $48) | Dana Whitfield / CFO | W5 report |
| Q-10 | Can the lab or production account allow Cognito, so the DEC-012 fallback isn’t needed in W4? | Tom Ngata | W4 Mon |

# Appendix B · Validation report

Generated by week2-milestone/build.py. Fixtures are converted with the rules in 06_SYNTHETIC_DATA_SHAPES.md and validated against contract/mcp_tools.schema.json.

## 1. Fixtures against the contract schema

| Record | Rows | Valid |
| --- | --- | --- |
| Claim | 20 | 20 |
| Policy (holder name dropped) | 15 | 15 |
| Document | 74 | 74 |

No schema violations.

Contract examples: §3.2 get_claim allowed example valid, §3.2 FORBIDDEN example valid

## 2. Cross-system invariants

| Invariant | Result |
| --- | --- |
| I-1 claim.policy_id exists | pass |
| I-2 VIN matches policy | pass |
| I-3 ACV matches policy | pass |
| I-4 document.claim_id exists | pass |
| I-5 no upload before incident | pass |
| I-6 Liability Only ⇒ no PD cover, null deductibles | pass |
| I-7 policy_start < policy_end | pass |
| I-8 exactly one FNOL per claim | pass |
| I-9 incident_type maps to loss_category | pass |
| I-10 users known to the identity pool | pass |

## 3. DEC-009 gate order over the eval cases (no model)

Agreement: 21/22. Net payable with the ACV cap and the deductible by loss category (DEC-010): 14/15 match.

| Case | Claim | Expected | Gates say | Gate fired | Match | Net payable |
| --- | --- | --- | --- | --- | --- | --- |
| W1-A01 | CLM-2024-1800 | approve | approve | 6 first-pass band | ✓ | 2700 ✓ |
| W1-A02 | SYN-W1-A02 | approve | approve | 6 first-pass band | ✓ | 1350 ✓ |
| W1-A03 | CLM-2024-2749 | approve | approve | 6 first-pass band | ✓ | 4200 ✓ |
| W1-A04 | CLM-2024-3041 | approve | approve | 6 first-pass band | ✓ | 4300 ✓ |
| W1-A05 | SYN-W1-A05 | approve | approve | 6 first-pass band | ✓ | 650 ✓ |
| W1-D01 | CLM-2024-2019 | deny | deny | 2 coverage | ✓ | — |
| W1-D02 | CLM-2024-2238 | deny | deny | 2 coverage | ✓ | — |
| W1-D03 | CLM-2024-2530 | deny | deny | 2 coverage | ✓ | — |
| W1-D04 | CLM-2024-2822 | deny | deny | 2 coverage | ✓ | — |
| W1-D05 | CLM-2024-2676 | deny | deny | 2 coverage | ✓ | — |
| W1-F01 | CLM-2024-2895 | flag_review | flag_review | 6 default | ✓ | 8700 ✓ |
| W1-F02 | CLM-2024-2311 | flag_review | flag_review | 5 documentation | ✓ | 17500 ✓ |
| W1-F03 | CLM-2024-2968 | flag_review | flag_review | 4 injury | ✓ | 13200 ✓ |
| W1-F04 | CLM-2024-2384 | flag_review | flag_review | 5 documentation | ✓ | 3100 ✓ |
| W1-F05 | SYN-W1-F05 | flag_review | deny | 2 coverage | ✗ | None ≠ 4900 |
| W1-R01 | CLM-2024-1873 | route_specialist | route_specialist | 1 fraud | ✓ | 30200 ✓ |
| W1-R02 | CLM-2024-2603 | route_specialist | route_specialist | 1 fraud | ✓ | 12150 ✓ |
| W1-R03 | CLM-2024-1946 | route_specialist | route_specialist | 3 total loss | ✓ | 16300 ✓ |
| W1-R04 | CLM-2024-3187 | route_specialist | route_specialist | 3 total loss | ✓ | 38250 ✓ |
| W1-R05 | CLM-2024-2457 | route_specialist | route_specialist | 3 total loss | ✓ | 24000 ✓ |
| W2-D06 | CLM-2024-3114 | deny | deny | 2 coverage | ✓ | — |
| W2-F06 | CLM-2024-2165 | flag_review | flag_review | 5 documentation | ✓ | — |

A disagreement here is not automatically a bug. W1-F05 is meant to disagree: the dates say the policy lapsed, and only reading the renewal-premium receipt shows it may not have. That is what Coverage Check is for. Any other disagreement means the labels or the gates are wrong, and it gets resolved in DECISIONS.md before Week 3.